## Product Log
CSCE 315-100 Programming Studio
Team 6 - Project 2 SCRUM Sprint 2 Product Log (Post Game Mechanics release)
Id | Story | Labels | Iteration | Iteration Start | Iteration End | Story Type | Estimate | Current State | Created at | Accepted at | Deadline | Requested By | Owned By | Description | URL | Comment | Comment | Task | Task Status | Task | Task Status | Task | Task Status
31127325 | start development document & report |  | 1 | 2012-06-11 | 2012-06-17 | bug |  | accepted | 2012-06-13 | 2012-06-15 |  | Daniel Tan | Daniel Tan
31241145 | Implement test telnet server code |  | 1 | 2012-06-11 | 2012-06-17 | feature | 3 | accepted | 2012-06-14 | 2012-06-16 |  | Phillip Ells | Phillip Ells
31240865 | Implement random position AI |  | 1 | 2012-06-11 | 2012-06-17 | feature | 2 | accepted | 2012-06-14 | 2012-06-17 |  | Phillip Ells | William Guerra
31191645 | the board can display the number of points for both black and white |  | 2 | 2012-06-18 | 2012-06-24 | feature | 1 | accepted | 2012-06-13 | 2012-06-19 |  | William Guerra | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31191645 | I didnt start it, but I had to to make this comment: it doesnt update (correctly) until next is entered (William Guerra - Jun 15, 2012)
31125355 | a player can choose the AI difficulty |  | 2 | 2012-06-18 | 2012-06-24 | feature | 1 | accepted | 2012-06-13 | 2012-06-19 |  | Daniel Tan | William Guerra |  | http://www.pivotaltracker.com/story/show/31125355 | Its very sassy (William Guerra - Jun 15, 2012) | Well, I lost it, but it is now rewritten. SLightly less sassy (William Guerra - Jun 16, 2012)
31327633 | Determine how many pieces are flipped for a move |  | 2 | 2012-06-18 | 2012-06-24 | feature | 3 | accepted | 2012-06-16 | 2012-06-19 |  | William Guerra | William Guerra |  | http://www.pivotaltracker.com/story/show/31327633
31481641 | Determine how many opponent moves are available after a move |  | 2 | 2012-06-18 | 2012-06-24 | feature | 2 | accepted | 2012-06-19 | 2012-06-19 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31481641
31338531 | Design general tree traversal |  | 2 | 2012-06-18 | 2012-06-24 | feature | 2 | accepted | 2012-06-17 | 2012-06-19 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31338531 | Design for min mobility AI (Daniel Tan - Jun 17, 2012) |  | Print out tree for a set search depth | not completed | Count the total opponent moves | not completed | Store the path of the lowest number of opponent moves | not completed
31449087 | AI can minimize opponent's mobility |  | 2 | 2012-06-18 | 2012-06-24 | feature | 3 | accepted | 2012-06-19 | 2012-06-19 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31449087
31481935 | More game engine testing |  | 2 | 2012-06-18 | 2012-06-24 | chore |  | accepted | 2012-06-19 | 2012-06-21 |  | Daniel Tan | William Guerra |  | http://www.pivotaltracker.com/story/show/31481935
31330693 | the game engine can run on a server |  | 2 | 2012-06-18 | 2012-06-24 | feature | 3 | accepted | 2012-06-16 | 2012-06-21 |  | Phillip Ells | Phillip Ells |  | http://www.pivotaltracker.com/story/show/31330693
31240065 | Additional: Play again dialogue after game ends |  | 2 | 2012-06-18 | 2012-06-24 | feature | 2 | accepted | 2012-06-14 | 2012-06-21 |  | Phillip Ells | William Guerra |  | http://www.pivotaltracker.com/story/show/31240065
31125339 | a player can turn the display on |  | 2 | 2012-06-18 | 2012-06-24 | feature | 1 | accepted | 2012-06-13 | 2012-06-21 |  | Daniel Tan | William Guerra |  | http://www.pivotaltracker.com/story/show/31125339
31125333 | a player can turn the display off |  | 2 | 2012-06-18 | 2012-06-24 | feature | 1 | accepted | 2012-06-13 | 2012-06-21 |  | Daniel Tan | William Guerra |  | http://www.pivotaltracker.com/story/show/31125333
31481815 | the printouts of the game are cleaner and contained in one place (optimize outputs) |  | 2 | 2012-06-18 | 2012-06-24 | feature | 2 | accepted | 2012-06-19 | 2012-06-21 |  | William Guerra | William Guerra |  | http://www.pivotaltracker.com/story/show/31481815
31481371 | each build name will have names rhyming with minnow |  | 2 | 2012-06-18 | 2012-06-24 | chore |  | accepted | 2012-06-19 | 2012-06-21 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31481371
31483333 | fix an issue with undo in hard AI |  | 2 | 2012-06-18 | 2012-06-24 | bug |  | accepted | 2012-06-19 | 2012-06-21 |  | Daniel Tan | Daniel Tan |  | http://www.pivotaltracker.com/story/show/31483333
31338411 | AI Final Release |  | 2 | 2012-06-18 | 2012-06-24 | release |  | accepted | 2012-06-17 | 2012-06-21 | 2012-06-22 | Daniel Tan |  |  | http://www.pivotaltracker.com/story/show/31338411

## Sprint 2 Burdown
Sprint 2 Burndown Chart